## How to use
Change request log
Log every request for work outside the signed scope on the day it arrives. Size it within two working days, then price it, trade it or decline it.
No work starts until the client approves in writing. Review this log in every weekly status report and reconcile it before each invoice.
Cells to edit: the cream cells on the Log sheet (blue text). White cells are formulas: do not overwrite them.
Row 2 of the Log sheet is a worked example; replace or delete it.
Status values: Logged, Sized, Priced, Approved, Declined, Traded, Delivered, Invoiced.
Price = estimated hours × rate. Approved-but-not-invoiced value is shown on the Summary sheet; it is margin at risk until billed.
Template by Aloka K · alokakiran.com · free to use and adapt

## Log
CR ID | Date raised | Raised by | Description | Type | Estimated hours | Rate per hour | Price | Decision / trade-off | Status | Approved by | Approval date | Invoice ref
CR-001 | 2026-10-05 | Client: eCommerce lead | Add a second shipping method for bulky items at checkout | Scope addition | 24 | 3500 | 84000 | Priced; delivered in sprint 14 | Approved | Head of Digital | 2026-10-08

## Summary
Change request summary
Total requests logged | 1
Approved, not yet invoiced (count) | 1
Approved, not yet invoiced (value) | 84000
Invoiced value | 0
Waiting for a decision (Logged, Sized or Priced) | 0
Declined | 0
Traded against existing scope | 0