## How to use
Hypercare exit checklist
Hypercare should end on written criteria, not on a date. For most commerce upgrades and re-platforms two to four weeks is enough.
Agree these criteria with the client before go-live, then review them daily during hypercare. Exit when every required item is Met.
Checklist sheet: edit the cream cells (owner, status, evidence). The readiness figure at the top is a formula.
Add or remove rows to suit the platform; keep the wording specific enough that 'Met' cannot be argued.
Template by Aloka K · alokakiran.com · free to use and adapt

## Checklist
Exit readiness (required items met) |  | 0%
Area | Exit criterion | Required | Owner | Status | Evidence / link | Notes
Stability | Zero open P1 or P2 defects | Yes
Stability | No production incidents in the last 5 business days | Yes
Journeys | Search, product page, cart and checkout stable for 5 business days | Yes
Journeys | Order export to ERP / OMS reconciled daily with no gaps | Yes
Performance | Page load and checkout times at or better than pre-go-live baseline | Yes
Commercial | Conversion rate and order volume within agreed range of baseline | Yes
Integrations | PIM, payment, tax and shipping integrations error-free in monitoring | Yes
Operations | Monitoring dashboards and alerts handed to the support team | Yes
Operations | Runbooks, release notes and environment documentation delivered | Yes
Operations | Known open items listed with owners and dates | Yes
Handover | Walkthrough held with the business-as-usual support team | Yes
Acceptance | Formal sign-off from the named client owner | Yes