## How to use
Weekly delivery KPI review
Eight numbers on one page, reviewed at the same time every week. The point is the trend: one red week is a conversation, three is an intervention.
Projects sheet: one row per active project. Edit the cream cells (blue text); burn %, margin variance and flags are formulas.
Utilisation sheet: one row per person. Edit available and billable hours; utilisation is calculated and coloured against the target in cell B1 of that sheet.
Row 2 on each sheet is a worked example; replace or delete it.
Targets used for colouring are my own operating benchmarks (utilisation 75-85%, margin variance within 5 points), not an industry survey. Change them to suit your practice.
Template by Aloka K · alokakiran.com · free to use and adapt

## Projects
Project | Budget hours | Hours burned | Burn % | % complete | Planned margin % | Actual margin % | Margin variance (pts) | Milestone RAG | Open P1/P2 | CRs awaiting decision | Unbilled amount | Client health (1-5) | Flag | Notes
Example: Adobe Commerce upgrade | 900 | 610 | 67.78% | 60% | 45% | 41% | -4 | Amber | 2 | 1 | 180000 | 4 | Watch | Burn ahead of progress; review estimate for checkout work

## Utilisation
Target utilisation (low / high) | 75% | 85% | My operating benchmark; edit to suit
Person | Role | Available hours | Billable hours | Utilisation | Status
Example: A. Sharma | Senior engineer | 40 | 33 | 82.5% | In range
Team total |  | 40 | 33 | 82.5%